## Slide 1: Operations Research Critical Path Method, PERT, & Min-cost Flow Problem
王 逸 琳 I-Lin Wang
ilinwang@mail.ncku.edu.tw
http://ilin.iim.ncku.edu.tw/
成功大學工業與資訊管理學系教授
作業研究

## Slide 2: Project Planning, Scheduling and Control
Planning: organized approach to accomplish the goal of minimizing elapsed time of project
  defines objectives and tasks;
  represents tasks interactions on a network;
  estimates time and resources
Scheduling: a time-phased commitment of resources
  identifies critical tasks which, if delayed, will delay the project’s completion time.
Control: means of monitoring and revising the progress of a project

## Slide 3: Project Management Graphs
Gantt Chart
  Detailed schedule for tasks
PERT diagram
  Precedence relation between tasks

## Slide 4: Network Representation of PERT diagram
Tasks (or activities) are represented by nodes (Activity On Node)
  Each task i has a duration denoted by di
  Node 1 represents the “start” and node n denotes the “finish” of the project
Precedence relations are shown by arcs
  specify what other tasks must be completed before the task in question can begin.
  form an acyclic graph (no directed cycles).
A path is a sequence of linked tasks (i.e., nodes) going from beginning to end
Critical path is the longest path in this acyclic graph
  Since there is no negative cycle, even Dijkstra’s algorithm can be used. Nevertheless, the “topological ordering algorithm” is more commonly used here.

## Slide 5: Precedence Examples
A
B
A
C
B
A
C
B
Activity B begins when activity A ends.
Activity C begins when both A & B end.
Both activities B & C can begin as soon as A ends.
tB ³ tA + dA
ti : starting times for task i,
tC ³ tA + dA
tC ³ tB + dB
tB ³ tA + dA
tC ³ tA + dA
tC ³ max{tA + dA , tB + dB}

## Slide 6: The Time to Complete a Project-1
To make the customer receive the adv by July 2, when should we start the whole process? Is June 2 ok?
3
2
4
2
3
2
3
1
5
2
10
A
B
C
D
E
F
G
H
I
J
K
 | Task | Day
A | Choose items from stock by dept manager | 3
B | Choose items to be brought in by buyers | 2
C | Choose & price items for adv by committee | 2
D | Prepare picture for sale item | 4
E | Prepare description for sale item | 3
F | Design adv | 2
G | Compile mailing list to send adv | 3
H | Print mailing labels | 1
I | Print adv | 5
J | Attach labels, stored adv by zip code | 2
K | Deliver adv | 10
Preceding Tasks
None
None
A,B
C
C
D,E
C
G
F
H,I
J
Notes: Buyer: 採買

## Slide 7: The Time to Complete a Project-2
3
2
4
2
3
2
3
1
5
2
10
A3
B2
C
D
E
F
G
H
I
J
K
3
2
4
2
3
2
3
1
5
2
10
A3
B2
C5
D9
E8
F
G8
H
I
J
K
3
2
4
2
3
2
3
1
5
2
10
A3
B2
C5
D9
E8
F11
G8
H9
I16
J18
K28
3
2
4
2
3
2
3
1
5
2
10
A3
B2
C5
D
E
F
G
H
I
J
K
C  max{3,2}+2
3
2
4
2
3
2
3
1
5
2
10
A3
B2
C5
D9
E8
F11
G8
H9
I
J
K
F  max{9,8}+2
3
2
4
2
3
2
3
1
5
2
10
A3
B2
C5
D9
E8
F11
G8
H9
I16
J18
K
J  max{9,16}+2
1.1: The Time to Complete a Project
Notes: Task Time Length Preceding Tasks
A Choose items by dept manager 3 days None
B Choose items by buyers 2 None
C Choose & price items for ads 2 A,B
D Prepare picture for sale item 4 C
E Prepare word for sale item 3 C
F Design adv 2 D,E
G Compile mailing list 3 C
H Print mailing labels 1 G
I Print adv 5 F
J Attach labels, stored by zip code 2 H,I
K Deliver adv 10 J

## Slide 8: Critical Path Analysis
At least need 28 days  June 2 is ok
Graph Properties:
  Appearance is not unique
  Acyclic
PERT: Program Evaluation and Review Technique (1958 US Navy Polaris submarine and missile project)
Hang up the destination node, the longest path == critical path
3
2
4
2
3
2
3
1
5
2
10
A3
B2
C5
D9
E8
F11
G8
H9
I16
J18
K28

## Slide 9: Acyclic PERT Diagram (Critical Path Method Network)
Theorem. If a network is acyclic, then the nodes can be labeled so that for each arc (i,j), i < j.
Such a node labeling is called a topological order.
1
2
5
4
3
6
7
8
5
1
3
2
1
1
2
4
7
3
6
If there is a cycle, e.g., 2-3-6-7-5-2, none of these 5 tasks could be scheduled first.

## Slide 10: Topological Sorting/Ordering
PERT: The tasks must be performed sequentially. We seek a total order T on the set of tasks containing the partial order R (by Hasse diagram). Such a process is called topological sorting (or ordering).
Topological sorting algorithm:
begin
initialization: calculate indeg(i) for each i in N; k:=1 add those nodes of zero indegree to LIST
while LIST is not empty do
choose (& remove) a node i from LIST
order(i)=k; k:=k+1
remove node i from N and its outgoing arcs from A
update indeg(i) & LIST for any remaining node i in N
end while
if N then the remaining graph contains a directed cycle
else we obtain an order(i) for each task i as its sequence to be done
end
given a PERT diagram G=(N,A), which is an AON (activity on node) graph
LIST : a node set storing zero-indegree nodes
i.e., minimal element in Hasse diagram

## Slide 11: Exercise on Topological Sorting
K
A
I
H
G
B
J
E
C
F
D
Action:
k=1: choose A (or B)
k=2: choose B (or A)
k=3: choose C
k=4: choose D (or E, or G)
k=5: choose E (or G)
k=6: choose F (or G)
k=7: choose I (or G)
k=8: choose G
k=9: choose H
k=10: choose J
k=11: choose K
Total Order:
A
AB
ABC
ABCD
ABCDE
ABCDEF
ABCDEFI
ABCDEFIG
ABCDEFIGH
ABCDEFIGHJ
ABCDEFIGHJK
There are many other possible sequences:
BACGHEDFIJK, ABCEDFGIHJK, ABCDGHEFIJK, ….

## Slide 12: Another application of topological sort
Consider an Excel spreadsheet
We say that cell A precedes cell B if cell B requires the value in cell A as part of its formula
This leads to a precedence graph for cells.
The precedence graph is acyclic (or else Excel reports an error).
Excel topologically sorts the cells, and then computes the values in cells in topological order.

## Slide 13: Formulating the CPM Problem
Input Data:
  PERT diagram, including the precedence relationships (i,j)A & durations di iN
Decision Variable:
  ti : the starting time for task i, iN
Objective: min tn- t1
  Minimize the elapsed time of the project (i.e., makespan) where node n is the last node in the graph
Constraint:
  tj ³ ti + di (i,j)A

## Slide 14: A Project Network Example
A,2
B,3
D,6
C,4
G,4
F,7
E,8
H,5
task
duration
Remark: the tasks are labeled alphabetically. If (i,j) is an arc then i < j.

## Slide 15: CPM LP Formulation
tA
tB
tC
tD
tE
tF
tG
tH
-1
1
0
0
0
0
0
0

2
(A, B)
0
-1
1
0
0
0
0
0

3
(B, C)
0
-1
0
1
0
0
0
0

3
(B, D)
0
0
-1
0
1
0
0
0

4
(C, E)
0
0
-1
0
0
1
0
0

4
(C, F)
0
0
0
-1
0
1
0
0

6
(D, F)
0
0
0
-1
0
0
1
0

6
(D, G)
0
0
0
0
-1
0
0
1

8
(E, H)
0
0
0
0
0
0
-1
1

4
(G, H)
Minimize tH -tA
Not a node-arc incidence matrix format ?
Check its transpose! One +1 & -1 each row !

## Slide 16: On the constraint matrix
tA
tB
tC
tD
tE
tF
tG
tH
-1
1
0
0
0
0
0
0

2
(A, B)
0
-1
1
0
0
0
0
0

3
(B, C)
0
-1
0
1
0
0
0
0

3
(B, D)
The constraint matrix is the transpose of a node-arc incidence matrix.
If we solve the linear program, the solution will be integer valued, assuming integral duration.
Note the time epoch variable ti here is NOT necessarily nonnegative. What matters is the relative time difference for consecutive tasks.

## Slide 17: Dual of the CPM LP
CPM Primal CPM Dual
Its dual LP seeks a “longest path” (i.e., the “critical path”). in the PERT diagram. Since this is an acyclic graph, we can ignore the “subtour” problem on general graphs.
Notes: If we set ti to be nonnegative, the dual constraint would be Sum(flow out of i) – Sum(flow into i) >= b_i
Then, stand on i=n, we know it has not flow goes out, which means the entering flow is at most 1 in total

## Slide 18: Critical Path Definitions
Earliest Start Time (ES)
  the earliest time a task can feasibly start
Earliest Finish Time (EF)
  the earliest time a task can feasibly end
Latest Start Time (LS)
  the latest time a task can feasibly start, without delaying the project
Latest Finish Time (LF)
  the latest time a task can feasibly end, without delaying the project

## Slide 19: Critical Path Method & Gantt Chart
Forward Pass
  Go through the jobs in order
  Start each job at the earliest time satisfying the precedence constraints
  It finds the earliest start and finish times
The Gantt Chart
  Lay out the tasks on a time line
  The width of the task is the amount of time it takes.
0
2
4
6
8
10
12
14
16
18
20
22
24
26
A
B

## Slide 20: A CPM Example: Forward Pass
A,2
B,3
D,6
C,4
G,4
F,7
E,8
H,5
Forward Pass
0
2
4
6
8
10
12
14
16
18
20
22
24
26
A
B
C
D
E
F
G
H

## Slide 21: CPM: The Backward Pass
Fix the finishing time (the one calculated by the Forward Pass)
Look at tasks in reverse order
Lay out tasks one at a time on the Gantt chart starting at the finish and working backwards to the start
Start the task at its latest starting time

## Slide 22: A CPM Example: Backward Pass
A,2
B,3
D,6
C,4
G,4
F,7
E,8
H,5
Backward Pass
0
2
4
6
8
10
12
14
16
18
20
22
24
26
A
B
C
D
E
F
G
H

## Slide 23: A CPM Example: Critical Path
The time to complete the schedule is at least as long as any path.
A,2
B,3
D,6
C,4
G,4
F,7
E,8
H,5
The length of A-B-C-F-H is 21 , NOT the longest one yet !
A-B-D-F-H is the longest path (critical path), with length 23.
The minimum makespan is the length of the critical path.

## Slide 24: Latest & earliest times, the critical path
Look for tasks of the same earliest & latest start times (i.e., slack = LS-ES = 0). These tasks are critical (NO slack), and are on a critical path. Here: A-B-D-F-H
0
2
4
6
8
10
12
14
16
18
20
22
24
26
C
E
A
B
D
F
G
H
0
2
4
6
8
10
12
14
16
18
20
22
24
26
A
B
C
D
E
F
G
H

## Slide 25: CPM Spreadsheet
If we “only” minimize the makespan, the LP may NOT necessarily put all the starting times at the earliest possible times. That is, those tasks not on the critical path may start late, as long as it does not affect the makespan.
You can “fool” the LP into giving the EST by minimizing the sum of completion times. (i.e., total waiting time)
Crashing an activity (task): Consider the possibility of reducing the final completion time by reducing the time of tasks but with some costs: reducing the duration of task j by xj units costs cj xj. Suppose the budget for reducing tasks is B.
spreadsheet

## Slide 26: More on Project Management
CPM
  Advantage of ease of use
  Lays out the Gantt chart (nicely visual)
  Identifies the critical path
  Used in practice on large projects
Other issues (drawbacks of CPM)
  Tasks take resources, which are limited  Resource Constrained
  Task times are really random variables
  Unpredictable things happen

## Slide 27: On variability of tasks
Consider 10 independent tasks
  each takes 1 unit of time on average
  the time it takes is uniformly distributed between 0 and 2.
CPM (uses expected value)
Modeling Randomness
The random schedule takes longer

## Slide 28: On Incorporating Variability
Program Evaluation and Review Technique (PERT)
  Attempts to incorporate variability in the durations
  Assume mean, m, and variance, s2, of the durations can be estimated
Simulation
  Model variability using any distribution
  simulate to see how long a schedule will take

## Slide 29: Incorporating Resource Constraints
Each task can have resources that it needs
  Renewable: People, equipment
  Unrenewable: budget, time
At any time, do not use more than available resources
  Makes the problem much more difficult to solve exactly. Heuristics are used.
Resource Constrained Project Scheduling Problem (RCPSP)
  Single mode vs. multi-mode (e.g., different skill sets, collaborative workers)

## Slide 30: Dealing with the unknown
VERY hard to model
  Require much training in Integer Programming modeling
How does one model totally unforeseen events?
  In the Big Dig, there is a leak in digging a tunnel despite assurances it would not happen
  In the Hubble telescope, a firm assures that the mirrors are ground properly. By the time the mistake is discovered, the telescope is in outer space.

## Slide 31: Minimum Cost Network Flows (MCF/MCNF)
Introduction to Minimum Cost Flows
Applications of Minimum Cost Flows
Structure of the Basis
Optimality Conditions
Obtaining Primal and Dual Solutions
Network Simplex Algorithm

## Slide 32: Minimum Cost Flow Problem
Determine a least cost shipment of a single commodity through a network in order to satisfy demands at certain nodes from available supplies at other nodes. Arcs have capacities and cost associated with them.
  Distribution of products
  Flow of items in a production line
  Routing of cars through street networks
  Routing of telephone calls
1
2
3
4
5
6
7
10
10
-5
-15
(2,5)
(5,3)
(4,6)
(2,4)
(1,3)
(1,1)
(3,2)
(4,2)
(6,4)
(2,6)
(6,5)
i
j
(cij, uij)
bi
bj

## Slide 33: Minimum Cost Flow Formulation
Given a digraph G=(N, A)
  Flow balance constraints: flow out - flow in = supply/demand
  Node types: Supply (bi > 0); Demand (bi < 0); Transshipment (bi = 0)
    Usually Total supply = Totally demand
  Flow bound constraints (lower & upper bound constraints)
    If lij>0, we may use replace xij by yij = xij - lij, for our own convenience.
  Shortest path, max flow, transportation & assignment problems are specialized MCF problems

## Slide 34: Common Assumptions
All data (cost, supply/demand, capacity) are integral.
The network is directed.
The sum of supplies equals the sum of demands, and the problem admits a feasible flow.
All arc costs are non-negative.
All arc have zero flow lower bound
  If not, we can easily convert it to be so.

## Slide 35: Distribution Problems
A car manufacturer has several manufacturing plants (p1,p2) and produces several car models (m1,m2,m3) at each plant that is shipped to various retailers (r1,r2). The manufacturer must determine the production plan for each model and shipping pattern that minimizes the overall cost of production and transportation.
r1
r2
p
1
p
2
p1/m1
p1/m2
p2/m1
p2/m2
p2/m3
r1/m1
r1/m2
r1/m3
r2/m1
r2/m2
Plant
nodes
Plant/model
nodes
Retailer/model
nodes
Retailer
nodes

## Slide 36: Properties of the Constraint Matrix
  xij has a “+1” in the ith row and a “-1” in the jth row.
  The n rows of the constraint matrix are linearly dependent.
  The rank of the constraint matrix is at most (n-1).
1
2
3
4
(15,50)
(25,30)
(15,40)
(25,20)
(15,30)
(5,10)
(15,50)
(5,60)
5
Spanning Tree  Triangular Basis
i
j
(cij, uij)
bi
bj
20
-5
10
-15
-10
r’2 := r2 + r1
r’3 := r3 + r’2
r’4 := r4 + r’3

## Slide 37: Properties of the Basis
THEOREM: There is a one-to-one correspondence between basis of the MCNF in G and spanning trees of G.
Triangularity property (or spanning tree property) allows us to speedup simplex computations substantially.
  the BFS can be calculated by traversing on a spanning tree (O(n) time)
Primal BFS (arc flow): BxB = b
Dual BFS (node potential, multiplier): BTpB = cB
UTpB= cB
UxB = b’

## Slide 38: Tree Traversal for Primal & Dual Variables
i
j
(cij, uij)
bi
bj
r’2 := r2 + r1
r’3 := r3 + r’2
r’4 := r4 + r’3
1
2
3
4
(15,50)
(25,30)
(15,40)
(25,20)
(15,30)
(5,10)
(15,50)
(5,60)
5
20
10
-15
-10
-5
Tree Traversal Algorithm for calculating the primal arc flow xij :
Start from a leaf: node 5  x45=15 node 3  x13=5
Trace up along tree arcs: node 4  x45 - x24 =10  x24=5
node 2  x24 - x12 = -10  x12=15 or node 1  x12 + x13 = 20  x12=15
1 | -1 | 0 | 0 | 0
1 | 0 | -1 | 0 | 0
0 | 1 | 0 | -1 | 0
0 | 0 | 0 | 1 | -1
Tree Traversal Algorithm for calculating the dual node potential pi :
Pick a node i and set its pi as any value: e.g., node 5 to have zero potential  p5=0
Trace up along tree arcs (zero reduced cost): arc (4,5)  5 - p4+ p5=0  p4=5
arc (2,4)  15 - p2+ p4=0  p2=20
arc (1,2)  25 - p1+ p2=0  p1=45
arc (1,3)  15 - p1+ p3=0  p3=30
This is because there exists a redundant row.
Notes: y1=25, y2=-10, y3=25, y4=5
y5=0, y4=5, y2=20, y1=45, y3=30
y1=0, y2=-25, y4=-40, y5=-45, y3=-15

## Slide 39: Spanning Tree Structure
MCNF is a special case of the bounded variable LP problem
Basic Arcs (T): Arcs in the spanning tree
NB Arcs at Lower Bounds (L): non-tree arcs with lower-bounded flow
NB Arcs at Upper Bounds (U): non-tree arcs with upper-bounded flow
(T, L, U): Basis structure or Spanning tree structure.
Feasible spanning tree structure
Optimal spanning tree structure

## Slide 40: Optimality Conditions
THEOREM: A spanning tree structure (T, L, U) is an optimal MCNF solution if it has a primal feasible arc flow x & a dual feasible node potential y such that each arc (i,j) whose reduced costs satisfy the following conditions:
PROOF: These are the LP optimality conditions specialized for MCNF.
Concept of to improve the current solution:
Whenever we find an arc (i,j) whose reduced cost violates the optimality condition
  (i,j)L with negative RC  we can “augment” flow along (i,j) to reduce the objective value
  (i,j)U with positive RC  we can “retreat” flow along (i,j) to reduce the objective value

## Slide 41: Network Simplex Algorithm
Algorithm network-simplex;
begin
determine the initial feasible tree structure (T, L, U);
let x be the arc flows and p be the node potentials;
while some nontree arc violates its optimality condition do
select an entering arc (k, l) violating its opt. condition;
add arc (k, l) to the tree and determine the leaving arc;
perform a tree update to update x and p;
end
No need to calculate the matrix inverse for B-1,
everything can be done by tree traversal !

## Slide 42: Construct the Initial Basis (similar to the Big-M)
Create G’ by
  Adding a dummy supply/demand supper node
  Adding artificial arcs from supply nodes to the supper node
  Adding artificial arcs from the supper node to demand nodes
All arcs in G have zero flow
Those artificial arcs makes an initial spanning tree (basis)
1
6
3
7
2
4
5
b(5)  0
b(4)  0
b(7)  0
b(3) < 0
b(6) < 0
b(2) < 0

## Slide 43: Entering Arc Selection
Optimality Conditions:
  check the reduced cost for a non-tree arc (i,j) such that
Eligible Arcs (to pivot in) :
  A non-tree arc with reduced cost such that
  For such a non-tree arc in L, we increase/augment flow
  For such a non-tree arc in U, we decrease/retreat flow

## Slide 44: Pivot Rules
Dantzig’s Pivot Rule:
  Select the arc with the maximum violation as the entering arc.
First Eligible Arc Pivot Rule:
  Select the first eligible arc found as the entering arc.
Candidate List Pivot Rule:
  Major iteration: Construct the candidate list.
  Minor iteration: Select an entering arc from the candidate list.

## Slide 45: Pivot Operation
Determine the pivot cycle W defined by the entering arc.
Determine the maximum flow d to augment along W.
  Example: d = min{u43-x43, u32-x32, u25-x25, x56, u69-x69, u94-x94}
  Degenerate iteration (d =0)
  Nondegenerate iteration (d >0)
Update the arc flows
  send flows along a negative cycle
Determine the leaving arc
Update the node potentials (on the circled one)
  Update p9 by with given p4 .
  Then we update p6 by p9 ; and then update p8 by p6 by tree traversal.
1
2
3
4
5
7
6
9
8
Entering arc
Apex

## Slide 46: Example of Network Simplex Algorithm
2
1
3
5
4
6
(3,8)
(2,3)
9
(2,3)
(2,2)
(4,3)
(4,6)
(5,4)
(3,5)
(5,7)
-9
i
j
bi
bj
(cij,uij)
i
j
pi
pj
xij
U arc
L arc
0
0
2
1
3
5
4
6
-10
-3
-8
-2
-6
7
2
2
5
5
4
2
0
0
2
1
3
5
4
6
0
-9
-3
-8
-2
-5
6
3
3
1
5
4
5
0
0
(3,5) enters basis
Retreat flow 5-3-1-2-5 for max {3, 3, 8-6, 2-1} = 1 unit
(2,5) leaves basis (in U)
Update p5 = -2 - 4 = -6 ; p6 = -6 - 4 = -10
(4,6) enters basis
Retreat flow 6-4-2-1-3-5-6 for max {5, 5, 7, 3-2, 3-2, 6-4} = 1 unit
(1,3) or (3,5) can leave basis (in U) say, (1,3) leaves basis to become U but (3,5) remains in T
Update p6 = -8 - 3 = -11 ; p5 = -11 + 4 = -7 ; p3 = -7 + 4 = -3 ;
A degenerate solution now
1 unit
1 unit
0
2
1
3
5
4
6
-11
-3
-8
-3
-7
6
3
3
4
4
5
2
0
0
Step 1
Step 2
Step 3
Satisfy Opt. Condition Optimal now!

## Slide 47
Q & A
Thanks!
I-Lin Wang (王逸琳)
Professor
Dept of Industrial & Information Management
National Cheng Kung University http://ilin.iim.ncku.edu.tw/